AI-Powered CAM Assistant

6-Month Development Roadmap — Phase 1: Foundation

Version 1.0   |   Q1–Q2 2026   |   Prepared for Internal Engineering & Product Teams

# Executive Summary

This document defines a concrete, executable 6-month roadmap for Phase 1 (Foundation) of the AI-powered CAM assistant project. The goal of this phase is to go from zero to a working prototype that can automatically recognize machining features from a real CAD model, generate basic machining strategies for prismatic parts, compute physics-based cutting parameters, and inject editable operations into Autodesk Fusion — demonstrating a credible end-to-end flow to investors and pilot customers.

The blueprint analysis identified five architectural modules: CAM integration, automatic feature recognition (AFR), AI strategy generation, cutting parameter optimization, and digital twin simulation. This 6-month plan focuses on modules 1, 2, and 4 — the minimum viable set needed to show real value — while laying technical foundations for the remaining modules.

| Target Platform | Autodesk Fusion (Python API) | End-State Demo | Prismatic part → auto-programmed toolpaths |
| --- | --- | --- | --- |
| Team Size | 4–5 engineers + 1 machining domain expert | Pilot Customer | 1 job shop, 10–20 parts by month 6 |

# Strategic Framing & Scope Decisions

Before detailing the plan, three critical scope decisions shape everything in this phase:

Decision 1: Autodesk Fusion First, Others Later

Fusion has a Python-native CAM API (adsk.cam) that allows creating setups, operations, and triggering toolpath generation programmatically — the fastest integration path. Mastercam and NX require C#/.NET and NXOpen respectively, adding ramp-up time. Fusion also has a large, growing user base in job shops (the primary target customer). NX integration is deferred to Phase 2.

Decision 2: Prismatic Parts Only in Month 1–6

Complex freeform and 5-axis strategies are deferred. Prismatic parts (pockets, slots, holes, steps, bosses, chamfers) represent ~60–70% of typical job shop work and are solvable with well-understood toolpath strategies. This scoping allows the team to build a polished, reliable experience rather than a broad, unreliable one.

Decision 3: Cloud AI, Local Fusion Plug-In

The Fusion plug-in will be a thin client: it extracts geometry and configuration, sends it to a cloud AI service (FastAPI on AWS), and injects results back into Fusion. This separates concerns cleanly — the AI engine can be iterated without re-deploying the plug-in, and compute-heavy physics simulation runs server-side. The API will be designed from Day 1 to be CAM-platform-agnostic.

# Team & Resourcing

The following roles are required for this 6-month phase. Roles can overlap in a small startup context, but domain expertise in machining physics is non-negotiable — this cannot be learned on the job.

| Role | Headcount | Core Responsibilities | When Needed |
| --- | --- | --- | --- |
| ML/AI Lead | 1 FT | AFR model design & training, strategy gen engine, surrogate model | Month 1 onward |
| Backend Engineer | 1 FT | Cloud API (FastAPI), physics engine (C++/Python), data pipelines | Month 1 onward |
| CAM Plug-In Engineer | 1 FT | Fusion Python API integration, UI overlay, result injection | Month 1 onward |
| Machining Domain Expert | 1 FT | Cutting parameter validation, strategy rules, shop-floor testing | Month 1 onward |
| ML Engineer (support) | 0.5 FT | Dataset generation, model training ops, evaluation harness | Month 2 onward |
| DevOps / Infra | 0.25 FT | AWS setup, CI/CD, security baseline | Month 1–2, then on-call |

Budget note: Total fully-loaded burn for this team (4.75 FTE) at market rates is approximately $250–350K for 6 months depending on geography and seniority. AWS compute for training and inference at this scale typically runs $2–5K/month.

MONTH 1 Infrastructure & Data Foundation ¦ Weeks 1–4

Month 1 is entirely about foundations. No user-visible features will exist by the end of this month, but the infrastructure that everything else builds on must be solid. A common failure mode in ML projects is spending months on model development only to discover the data pipeline or deployment infrastructure is broken. Month 1 eliminates that risk.

Engineering Tasks

| Task | Owner / Role | Deliverable | Success Metric |
| --- | --- | --- | --- |
| Stand up AWS infrastructure (VPC, ECS/EC2, RDS, S3) | DevOps | Deployed cloud environment with CI/CD pipeline | API health check passes; infra documented |
| Set up FastAPI skeleton with Fusion plug-in handshake endpoint | Backend Eng | REST API with /health, /analyze, /generate stubs | Fusion plug-in can POST a ping and receive response |
| Build Fusion plug-in scaffold: extract STEP geometry from active model | CAM Plug-In Eng | Fusion plug-in that extracts B-Rep / STEP and sends to API | 5 test models extracted correctly |
| Synthetic CAD dataset generation pipeline using pythonOCC | ML Engineer | 1,000 diverse prismatic part CAD files with feature labels | Dataset passes variety and correctness audit by domain expert |
| Define feature taxonomy: 12–15 prismatic feature types with dimensions | Domain Expert + ML Lead | Feature ontology document + label schema | Sign-off from machining expert; maps to machining op types |
| Set up PyTorch Geometric environment + B-Rep to graph converter | ML Lead | pythonOCC → face-edge graph pipeline | 10 sample models converted; graphs visually verified |

End of Month 1 Gate

- Fusion plug-in successfully extracts geometry from 3 real CAD models

- Cloud API is live and reachable from Fusion

- Synthetic dataset of 1,000 labeled parts exists in S3

- B-Rep → graph conversion working for all 1,000 parts

MONTH 2 Automatic Feature Recognition — Training ¦ Weeks 5–8

Month 2 focuses on training the first version of the AFR model. The goal is not perfection — it is a trained model that demonstrates the approach works and establishes a performance baseline. Research benchmarks show >97% accuracy with HGCNN on clean datasets; realistically, the first internal model will achieve 80–85% on the held-out test set, which is sufficient to proceed.

Engineering Tasks

| Task | Owner / Role | Deliverable | Success Metric |
| --- | --- | --- | --- |
| Train baseline HGCNN model on 1,000-part synthetic dataset | ML Lead + ML Eng | Trained AFR model checkpoint + evaluation report | >80% per-feature classification accuracy on held-out set |
| Expand synthetic dataset to 5,000 parts with more complex intersecting features | ML Engineer | 5,000-part training corpus in S3 | Dataset diversity score reviewed by domain expert |
| Implement dimension extraction module: extract depth, width, diameter from recognized features | ML Lead | Dimension extraction pipeline integrated with AFR model | <10% mean relative error on 50 test features |
| Integrate AFR model into cloud API: /analyze endpoint live | Backend Eng | POST /analyze → returns JSON feature list with dimensions | API processes a STEP file in <5 seconds |
| Fusion plug-in: display recognized features overlaid on model | CAM Plug-In Eng | Visual feature overlay in Fusion viewport | Domain expert can verify feature detections visually |
| Collect 20 real customer parts from pilot shop (with permission) | Domain Expert | 20 real-world STEP files + machining intent documentation | Parts span at least 8 feature types from taxonomy |

End of Month 2 Gate

- AFR model correctly identifies features on at least 15 of 20 real shop parts

- /analyze endpoint returns results in under 5 seconds

- Feature overlay visible in Fusion for a test user

MONTH 3 Cutting Parameter Physics Engine ¦ Weeks 9–12

Month 3 builds the cutting parameter optimizer — the module that computes feeds, speeds, depth of cut, and stepover for each recognized feature. This is the most domain-knowledge-intensive component. The machining domain expert leads this month, with the backend engineer implementing the C++ mechanics. The approach follows the Altintas/Budak mechanistic force model, which is well-documented in academic literature and has known coefficients for common materials.

Engineering Tasks

| Task | Owner / Role | Deliverable | Success Metric |
| --- | --- | --- | --- |
| Implement mechanistic cutting force model in C++ (chip load, radial/axial engagement, tangential forces) | Backend Eng + Domain Expert | C++ library with Python bindings for force prediction | Force predictions within 15% of published empirical data for aluminum 6061 |
| Build material database: aluminum alloys, mild steel, 304 stainless (start here) | Domain Expert | JSON material database with force coefficients and tool wear constants | Validated against Sandvik/Kennametal published data |
| Implement extended Taylor tool life equation with feed/doc corrections | Backend Eng | Tool life prediction function integrated into C++ engine | Tool life estimates within 20% of published data |
| Build tool library importer: read Fusion tool library XML/JSON | CAM Plug-In Eng | Tool library parser that extracts diameter, flutes, coating, substrate | Correctly parses 3 common Fusion tool libraries |
| Implement multi-objective optimizer: minimize cycle time subject to force, surface Ra, and power constraints | Backend Eng + ML Lead | Optimizer that returns Pareto-optimal feeds/speeds given feature + tool + material | Outputs reasonable parameters validated by domain expert on 10 test cases |
| Expose /parameters endpoint in cloud API | Backend Eng | POST /parameters → returns feeds, speeds, depth of cut, stepover per feature | End-to-end test: STEP file in → parameters out in <10 seconds |

End of Month 3 Gate

- Domain expert validates cutting parameters for aluminum on 10 test features as 'would use these in production'

- Physics engine runs in under 2 seconds per feature

- Tool library import working from a real Fusion tool library

MONTH 4 Strategy Generation & CAM Injection ¦ Weeks 13–16

Month 4 is the critical integration month. The strategy generation engine assembles recognized features + cutting parameters into a sequenced machining plan, and the Fusion plug-in injects the result as actual, editable CAM operations. This is the first time the end-to-end flow is visible inside a real CAM environment — a major internal milestone.

Engineering Tasks

| Task | Owner / Role | Deliverable | Success Metric |
| --- | --- | --- | --- |
| Build rule-based strategy sequencer for prismatic features (roughing before finishing, accessibility checks, operation ordering) | Domain Expert + Backend Eng | Strategy sequencer that takes feature list → ordered operation list | Correct operation sequence on 20 test parts (verified by domain expert) |
| Implement tool selection logic: for each feature + material, select best available tool from library | Domain Expert + ML Lead | Tool selector module integrated into strategy engine | Tool selections validated as correct on 20 test cases |
| Implement Fusion API operation injection: create 2D Pocket, 2D Contour, Drilling operations with computed parameters | CAM Plug-In Eng | Fusion plug-in that creates native operations from API response | Operations appear in Fusion CAM browser, toolpaths generate successfully |
| Build approach direction analysis: determine optimal setup orientation per feature group | ML Lead + Domain Expert | Setup planner that groups features by machinable direction | Correct setup count on 15 test parts |
| Create Fusion side panel UI: show analysis status, feature list, 'Generate' button, progress indicator | CAM Plug-In Eng | Working Fusion plug-in UI panel | Non-technical tester can use it without instructions |
| End-to-end integration test: one click to go from open model to populated CAM tree | All | Working demo video of full flow on 3 sample parts | Operations generate without errors; cycle time estimate shown |

End of Month 4 Gate

- Full end-to-end flow working: STEP model → feature recognition → parameters → Fusion operations injected

- Demo recorded and reviewed internally

- Pilot shop contact previews demo and provides written feedback

MONTH 5 Pilot Testing & Refinement ¦ Weeks 17–20

Month 5 shifts the team's primary focus from building to testing with real users. The pilot shop partner uses the plug-in on 10–15 real production parts and documents everything that breaks, confuses, or produces wrong results. Simultaneously, the engineering team establishes the feedback data pipeline that will power continuous improvement in later phases.

Engineering Tasks

| Task | Owner / Role | Deliverable | Success Metric |
| --- | --- | --- | --- |
| Deploy plug-in to pilot shop; provide onboarding session | Domain Expert + CAM Plug-In Eng | Pilot shop actively using the tool on real parts | Pilot shop completes first 5 parts with tool |
| Implement structured feedback collection: rate each operation (correct / needs tweak / wrong) | Backend Eng + CAM Plug-In Eng | In-plug-in rating widget + backend logging to database | Feedback records stored with part geometry and AI outputs |
| AFR model refinement: retrain on 5,000 parts + 20 real pilot parts; address observed failure modes | ML Lead + ML Eng | AFR v2 model checkpoint | >90% accuracy on pilot part set |
| Cutting parameter corrections: update coefficients based on pilot shop actual machining results | Domain Expert + Backend Eng | Calibrated material database with pilot-shop-validated constants | Parameters produce acceptable surface finish on 8 of 10 pilot parts |
| Add basic collision avoidance check: flag tool holder vs. fixture clearance issues before injection | Backend Eng | Collision pre-check module with warning in Fusion UI | Correctly flags 5 seeded collision scenarios |
| Performance optimization: reduce end-to-end API latency to <15 seconds for typical parts | Backend Eng | Profiled and optimized API with benchmarks | P90 latency <15s on 20 representative test parts |

End of Month 5 Gate

- Pilot shop has used tool on minimum 10 real parts

- Domain expert rates generated parameters as 'usable without significant changes' on 8 of 10 parts

- Feedback database populated with 50+ operation ratings

MONTH 6 Stabilization, Metrics & Phase 2 Prep ¦ Weeks 21–24

Month 6 is about hardening what was built, quantifying results against benchmark targets, and documenting the architecture cleanly so Phase 2 can begin without technical debt. A key deliverable is the phase-end performance report that answers: did we hit the targets from the blueprint?

Engineering Tasks

| Task | Owner / Role | Deliverable | Success Metric |
| --- | --- | --- | --- |
| Run formal benchmark: measure programming time reduction on 20 standard parts vs. manual baseline | Domain Expert + All | Benchmark report with time measurements | Demonstrate ≥50% programming time reduction (target 80% by Phase 4) |
| Implement cycle time estimation: sum operation times using machine feed rates and path lengths | Backend Eng | Cycle time display in Fusion side panel | Estimates within 20% of actual machine runtime on 10 test parts |
| Documentation: API spec (OpenAPI), plug-in architecture, model cards for AFR model | All | Technical documentation in Confluence/Notion | New engineer can set up dev environment in <2 hours using docs |
| Security audit: review API authentication, data handling, and STEP file storage policies | Backend Eng + DevOps | Security review report + remediation log | No critical findings outstanding |
| Phase 2 planning: design NX integration architecture, 5-axis strategy spec, and surrogate model training plan | ML Lead + Domain Expert | Phase 2 technical spec document | Reviewed and approved by team |
| Investor / customer demo preparation: polish UI, record demo video of best-case flow | All | Demo video + pitch deck data slide | Demo reviewed and approved by founders/stakeholders |

End of Month 6 Gate (Phase 1 Complete)

- End-to-end flow reliable on ≥80% of submitted prismatic parts

- Programming time reduction ≥50% demonstrated on 20-part benchmark

- 1 paying or LOI-signed pilot customer

- All documentation complete; Phase 2 spec written

# Milestone & Gate Summary

| Month | Key Milestone | Gate Criteria |
| --- | --- | --- |
| 1 | Cloud API + Fusion geometry extraction working; synthetic dataset generated | Plug-in can send/receive data; 1,000 labeled parts in S3 |
| 2 | AFR model trained; feature detection live in Fusion UI | >80% accuracy on held-out set; visual overlay working |
| 3 | Physics engine computing cutting parameters for Al + steel | Domain expert validates parameters on 10 test features |
| 4 | End-to-end demo: model → Fusion operations in one click | 3 parts demo'd without manual errors; pilot shop previews |
| 5 | Pilot shop actively using tool on real production parts | 10 parts processed; 8 rated 'usable'; feedback pipeline live |
| 6 | Phase 1 complete: benchmarked, documented, Phase 2 scoped | ≥50% time reduction demonstrated; 1 pilot customer committed |

# Risks & Mitigation

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Fusion CAM API cannot inject operations with custom parameters | Medium | High | Test Fusion API injection in Week 1 as a spike. Fallback: generate a Fusion script file the user runs manually. Escalate to Autodesk partner program for API access if needed. |
| AFR model accuracy insufficient on real-world parts (mesh quality, STEP variability) | High | High | Begin collecting real customer STEP files in Month 2. Allocate 20% of Month 3 to data cleaning and model robustness. Set accuracy floor of 75% as minimum viable. |
| Domain expert unavailable or insufficient depth | Medium | Critical | Hire machinist consultant with CNC programming experience as non-negotiable. Budget 2–3 weeks for knowledge capture into structured rule sets before this becomes a bottleneck. |
| Physics model diverges from real cuts (material variability, tool wear) | High | Medium | Frame physics model as 'starting point, not gospel.' Let users tweak parameters and log edits as ground truth for ML refinement in Phase 3. |
| Pilot shop not engaged or parts too complex for Phase 1 scope | Medium | Medium | Screen pilot shop in Month 1. Provide 5–10 representative 'compatible' part files they can use immediately. Set expectations clearly: 'works on prismatic parts in aluminum and mild steel.' |
| 6-month timeline overruns due to technical complexity | Medium | Medium | Months 1–3 are largely sequential and lower-risk. Months 4–5 carry the most integration risk. Build a 2-week buffer into Month 4 by reducing Month 5 scope if needed (defer collision check to Phase 2). |

# Technology Stack — Phase 1

| Component | Technology | Rationale |
| --- | --- | --- |
| CAM Plug-In | Python, adsk.cam (Fusion API) | Native Python support; fastest integration path for Fusion |
| Cloud API | Python FastAPI on AWS ECS (Fargate) | High performance, auto-scaling, async support |
| Feature Recognition | PyTorch Geometric + pythonOCC | GNN on B-Rep graphs; pythonOCC for STEP parsing |
| Physics Engine | Custom C++ with pybind11 Python bindings | Mechanistic force models require low-level performance |
| Optimization | SciPy (SLSQP), custom Pareto front | Mature, well-documented, sufficient for Phase 1 |
| Data Storage | PostgreSQL (RDS) + S3 | Relational for jobs/feedback; S3 for geometry files |
| Model Training | AWS SageMaker (spot instances) | Cost-effective GPU training for GNN models |
| CI/CD | GitHub Actions + Docker + ECR | Standard, easy to maintain at small team scale |

# Explicitly Out of Scope for Phase 1

The following items are deferred to Phases 2–4. Being explicit about scope prevents scope creep and keeps the team focused on demonstrable value.

- NX and Mastercam integration (Phase 2)

- 5-axis and 3+2 axis strategies (Phase 3)

- Reinforcement learning strategy optimization (Phase 3)

- Real-time sensor feedback and digital twin (Phase 3–4)

- Fixture and soft jaw design automation (Phase 3)

- Freeform surface machining (Phase 4)

- Multi-tenant enterprise deployment / SSO (Phase 4)

- SOC 2 / ISO 27001 certification (Phase 4)

# Definition of Success

Phase 1 is a success if, at the end of Month 6, a machinist at the pilot shop can open a new aluminum prismatic part in Autodesk Fusion, click 'Generate' in the CAM Assistant panel, and have a fully populated CAM tree with reasonable operations and cutting parameters in under 30 seconds — saving at least 1–2 hours compared to manual programming. Everything in this 6-month plan is oriented toward making that single scenario work reliably.

The 80% programming time reduction target in the blueprint is a Phase 4 goal. A credible 50% reduction by Month 6 on a narrow scope is a stronger foundation than a fragile 80% on paper.